## Cover Sheet
ASSIGNMENT 1
DO INITIAL VERSION OF PERSONAL WBS
CSE 6329
Software Metrics and Quality Engineering
Spring, 2017
Name | VISHWEKAR ADITYA
ID | 1001228861
Points
(/10) Correct Format, including name on top, totals, etc.
(/50) Reasonable list of tasks for each assignment
(/40) Reasonable estimates, actual and earned hours.
(100) Total Assignment Grade
Comments from Grader
1

## Instructions
Instructions for Weekly WBS Entries
General Rules:
1: Cells with a white background are cells in which you may put a number or a task name at the appropriate time.
Some of these cells will change color when you put something there.
2: Cells with a colored background usually contain formulas that you should not change unless you are extending
the length of the course (which you may only do with the instructor's permission).
3: You may insert rows as needed to accommodate all of the tasks that you plan to do for the course.
(Use the spare tasks near the bottom to preserve the correct format and formulas.)
4: You should study every formula and every graph and understand what it is and why. This may be on an exam.
Step 1 - Enter hours worked each week
At the end of each week, fill in hours worked on each task, as follows:
(hours may be entered in whole hours, such as 2, or in tenths of an hour, such as 1.3)
For each task:
If you did no work on that task, do nothing.
If you worked on that task during the past week:
Enter total hours worked on the task in the column corresponding to the current week (column U through AJ).
Cell should change color when you enter a non-zero value.
Enter total hours of work remaining on the task in column E:
If the task is complete, enter 0 hours remaining.
The total hours remaining is your best current estimate, which may differ from what was originally estimated.
Step 2: Check for errors
Review all totals and numbers and make sure everything seems correct.
Make corrections as necessary
If the graphs (charts) look strange, something is wrong. Figure out what's wrong and fix it.
Step 3: Record Estimated Hours Remaining at end of current week
Copy the "total estimated hours remaining" (bottom of column E) to estimated hours remaining cell for current week
Cell will change color
This will update the burndown and burnup charts
Step 4: Update Earned Value
The hours earned this week row for the current week (near the bottom) should start off with blank or 0.
For each task that has completed during the current week:
Find the originally estimated hours for that task and add it to the hours earned this week for the current week
When done, this total will be the earned value for the week and will update the earned value chart accordingly.

## WBS
|  | PWBS | [10 empty] | Planned Effort |  | 3.95 | 3.95 | 3.95 | 3.95 | 3.95 | 3.95 | 3.95 | 3.95 | 3.95 | 3.95 | 3.95 | 3.95 | 3.95 | 3.95 | 3.95 | 3.95 |  | 63.2
Open | 2017 sp | CSE 6329-002 | Schedule | [9 empty] | Cumulative Plan (PV) |  | 3.95 | 7.9 | 11.85 | 15.8 | 19.75 | 23.7 | 27.65 | 31.6 | 35.55 | 39.5 | 43.45 | 47.4 | 51.35 | 55.3 | 59.25 | 63.2
In Progress | VISHWEKAR ADITYA | [11 empty] | Estimated Effort Remaining | 63.2 | 59.25 | 55.3 | 51.35 | 47.4 | 43.45 | 39.5 | 35.55 | 31.6 | 27.65 | 23.7 | 19.75 | 15.8 | 11.85 | 7.9 | 3.95 | 1.3323e-14
Complete | Actual Results |  |  | Estimates |  | WBS | [8 empty] | Actual Hours Worked and Earned
Status | Estimated Hours Remaining | Actual Hours So Far | Actual Completion Week | Estimated Hours of Effort | Planned Completion Week | Task # | [6 empty] | Task Description Week Ending >> |  | 2017-01-27 | 2017-02-03 | 2017-02-10 | 2017-02-17 | 2017-02-24 | 2017-03-03 | 2017-03-10 | 2017-03-17 | 2017-03-24 | 2017-03-31 | 2017-04-07 | 2017-04-14 | 2017-04-21 | 2017-04-28 | 2017-05-05 | 2017-05-12 | insert new column here | Total Hours Worked
[6 empty] | 100000 | A1 - Develop PWBS
[6 empty] | 110000 |  | Read and Analyze A1 SOW for PWBS
Complete | 0 | 0.5 |  | 0.5 |  | 111000 |  |  | List tasks to be performed | [5 empty] | 2017-01-27: 0.5 |  | 0.5
Complete | 0 | 0.4 |  | 0.4 |  | 112000 |  |  | Estimate hours required for each task | [5 empty] | 2017-01-27: 0.4 |  | 0.4
Complete | 0 | 0.6 |  | 0.6 |  | 113000 |  |  | Break into smaller sub-tasks as required | [5 empty] | 2017-01-27: 0.6 |  | 0.6
Complete | 0 | 0.3 |  | 0.3 |  | 114000 |  |  | Modify template to add tasks and correct formulas/coloring | [5 empty] | 2017-01-27: 0.3 |  | 0.3
Complete | 0 | 0.2 |  | 0.2 |  | 115000 |  |  | Record estimated hours in Estimated Hours of Effort column | [5 empty] | 2017-01-27: 0.2 |  | 0.2
[6 empty] | 120000 |  | Read and Analyze A2 SOW
Complete | 0 | 0.4 |  | 0.6 |  | 121000 |  |  | List tasks to be performed | [5 empty] | 2017-01-27: 0.4 |  | 0.4
Complete | 0 | 0.3 |  | 0.3 |  | 122000 |  |  | Estimate hours required for each task | [5 empty] | 2017-01-27: 0.3 |  | 0.3
Complete | 0 | 0.3 |  | 0.4 |  | 123000 |  |  | Break into smaller sub-tasks as required | [5 empty] | 2017-01-27: 0.3 |  | 0.3
Complete | 0 | 0.3 |  | 0.2 |  | 124000 |  |  | Modify template to add tasks and correct formulas/coloring | [5 empty] | 2017-01-27: 0.3 |  | 0.3
Complete | 0 | 0.2 |  | 0.2 |  | 125000 |  |  | Record estimated hours in Estimated Hours of Effort column | [5 empty] | 2017-01-27: 0.2 |  | 0.2
[6 empty] | 130000 |  | Read and Analyze A3 SOW
Complete | 0 | 0.3 |  | 0.5 |  | 131000 |  |  | List tasks to be performed | [5 empty] | 2017-01-27: 0.3 |  | 0.3
Complete | 0 | 0.3 |  | 0.4 |  | 132000 |  |  | Estimate hours required for each task | [5 empty] | 2017-01-27: 0.3 |  | 0.3
Complete | 0 | 0.2 |  | 0.2 |  | 133000 |  |  | Break into smaller sub-tasks as required | [5 empty] | 2017-01-27: 0.2 |  | 0.2
Complete | 0 | 0.2 |  | 0.3 |  | 134000 |  |  | Modify template to add tasks and correct formulas/coloring | [5 empty] | 2017-01-27: 0.2 |  | 0.2
Complete | 0 | 0.2 |  | 0.2 |  | 135000 |  |  | Record estimated hours in Estimated Hours of Effort column | [5 empty] | 2017-01-27: 0.2 |  | 0.2
[6 empty] | 140000 |  | Read and Analyze A4 SOW
Complete | 0 | 0.3 |  | 0.5 |  | 141000 |  |  | List tasks to be performed | [5 empty] | 2017-01-27: 0.3 |  | 0.3
Complete | 0 | 0.2 |  | 0.3 |  | 142000 |  |  | Estimate hours required for each task | [5 empty] | 2017-01-27: 0.2 |  | 0.2
Complete | 0 | 0.2 |  | 0.2 |  | 143000 |  |  | Break into smaller sub-tasks as required | [5 empty] | 2017-01-27: 0.2 |  | 0.2
Complete | 0 | 0.2 |  | 0.3 |  | 144000 |  |  | Modify template to add tasks and correct formulas/coloring | [5 empty] | 2017-01-27: 0.2 |  | 0.2
Complete | 0 | 0.3 |  | 0.2 |  | 145000 |  |  | Record estimated hours in Estimated Hours of Effort column | [5 empty] | 2017-01-27: 0.3 |  | 0.3
Complete | 0 | 0.3 |  | 0.3 |  | 150000 |  | Enter Actual and Earned Hours for week ending 1/27 | [6 empty] | 2017-01-27: 0.3 |  | 0.3
Complete | 0 | 0.2 |  | 0.1 |  | 151000 |  | Submit A1 (Draft) | [6 empty] | 2017-01-27: 0.2 |  | 0.2
Open | 1.2 | 0 |  | 1.2 |  | 160000 |  | Review comments from TA/Instructor and Correct Mistakes | [23 empty] | 0
[6 empty] | 170000 |  | Make Weekly Updates to Actual and Earned Hours in PWBS
Open | 0.5 | 0 |  | 0.5 |  | 171000 |  |  | Updates for 2/3 | [22 empty] | 0
Open | 0.5 | 0 |  | 0.5 |  | 172000 |  |  | Updates for 2/10 | [22 empty] | 0
Open | 0.7 | 0 |  | 0.7 |  | 173000 |  |  | Updates for 2/17 | [22 empty] | 0
Open | 0.8 | 0 |  | 0.8 |  | 174000 |  |  | Updates for2/24 | [22 empty] | 0
Open | 0.4 | 0 |  | 0.4 |  | 175000 |  |  | Updates for 3/3 | [22 empty] | 0
Open | 0.5 | 0 |  | 0.5 |  | 176000 |  |  | Updates for 3/10 | [22 empty] | 0
Open | 0.6 | 0 |  | 0.6 |  | 177000 |  |  | Updates for 3/17 | [22 empty] | 0
Open | 0.7 | 0 |  | 0.7 |  | 178000 |  |  | Updates for 3/24 | [22 empty] | 0
Open | 0.5 | 0 |  | 0.5 |  | 179000 |  |  | Updates for 3/31 | [22 empty] | 0
Open | 0.4 | 0 |  | 0.4 |  | 179100 |  |  | Updates for 4/7 | [22 empty] | 0
Open | 0.5 | 0 |  | 0.5 |  | 179200 |  |  | Updates for 4/14 | [22 empty] | 0
Open | 0.5 | 0 |  | 0.5 |  | 179300 |  |  | Updates for 4/21 | [22 empty] | 0
Open | 1.2 | 0 |  | 1.2 |  | 179400 |  |  | Updates for 4/28 | [22 empty] | 0
Open | 0.2 | 0 |  | 0.2 |  | 180000 |  | Submit Final PWBS | [23 empty] | 0
[6 empty] | 200000 | A2 - Analysis of Defect Data
[6 empty] | 210000 |  | Read and Analyze A2 SOW
[6 empty] | 211000 |  |  | Post-Release Quality
[6 empty] | 211100 |  |  |  | Post-Release Quality for Product A Graph
Open | 0.4 | 0 |  | 0.4 |  | 211110 |  |  |  |  | Analyze 1 year data of Product A | [20 empty] | 0
Open | 0.5 | 0 |  | 0.5 |  | 211120 |  |  |  |  | Discuss basic facts about the post-release quality graph | [20 empty] | 0
[6 empty] | 211200 |  |  |  | Post-Release Quality Average Graph
Open | 0.6 | 0 |  | 0.6 |  | 211210 |  |  |  |  | Calculate average number of defects per product | [20 empty] | 0
Open | 0.4 | 0 |  | 0.4 |  | 211220 |  |  |  |  | Discuss, how product ‘A’ compares with the average | [20 empty] | 0
[6 empty] | 211300 |  |  |  | Post-Release Quality Average Normalized by Size Graph
Open | 0.5 | 0 |  | 0.5 |  | 211310 |  |  |  |  | Calculate average for all products normalized by size | [20 empty] | 0
Open | 0.3 | 0 |  | 0.3 |  | 211320 |  |  |  |  | Discuss and analyze reasons for normalization | [20 empty] | 0
[6 empty] | 211400 |  |  |  | Post-Release Quality by Development Process Graph
[6 empty] | 211410 |  |  |  |  | Calculate average for all products w.r.t. SCRUM and XP
Open | 0.4 | 0 |  | 0.4 |  | 211411 | [5 empty] | Calculate total defects per KLOC w.r.t. Extreme Programming | [19 empty] | 0
Open | 0.4 | 0 |  | 0.4 |  | 211412 | [5 empty] | Calculate total defects per KLOC w.r.t. SCRUM | [19 empty] | 0
Open | 0.4 | 0 |  | 0.4 |  | 211413 | [5 empty] | Calculate total uncorrected defects w.r.t Extreme Programming | [19 empty] | 0
Open | 0.5 | 0 |  | 0.5 |  | 211414 | [5 empty] | Calculate total uncorrected defects w.r.t. SCRUM | [19 empty] | 0
Open | 0.4 | 0 |  | 0.4 |  | 211420 |  |  |  |  | Discuss the differences and its significance based on SCRUM and XP | [20 empty] | 0
[6 empty] | 211500 |  |  |  | Post-Release Quality by Programming Language Graph
[6 empty] | 211510 |  |  |  |  | Calculate average for all products w.r.t. Python and C language
Open | 0.5 | 0 |  | 0.5 |  | 211511 | [5 empty] | Calculate total defects per KLOC w.r.t. Python project | [19 empty] | 0
Open | 0.5 | 0 |  | 0.5 |  | 211512 | [5 empty] | Calculate total defects per KLOC w.r.t. C project | [19 empty] | 0
Open | 0.6 | 0 |  | 0.6 |  | 211513 | [5 empty] | Calculate total uncorrected defects w.r.t Python project | [19 empty] | 0
Open | 0.5 | 0 |  | 0.5 |  | 211514 | [5 empty] | Calculate total uncorrected defects w.r.t. C project | [19 empty] | 0
Open | 0.4 | 0 |  | 0.4 |  | 211520 |  |  |  |  | Discuss the differences and its significance based on Python and C | [20 empty] | 0
[6 empty] | 211600 |  |  |  | Device graph based on significant data
Open | 0.4 | 0 |  | 0.4 |  | 211610 |  |  |  |  | Use statistical function to examine data and find significant information | [20 empty] | 0
Open | 0.4 | 0 |  | 0.4 |  | 211620 |  |  |  |  | Discuss the information depicted in graph & methods used. | [20 empty] | 0
[6 empty] | 220000 |  | Post-Release Quality History
[6 empty] | 221000 |  |  | Graph 1 by quarter for 3 years
Open | 0.5 | 0 |  | 0.5 |  | 221100 |  |  |  | Analyse and display the metric based on quarters | [21 empty] | 0
Open | 0.4 | 0 |  | 0.4 |  | 221200 |  |  |  | Review among the software team. | [21 empty] | 0
[6 empty] | 222000 |  |  | Graph 2 by year for 3 years
Open | 0.5 | 0 |  | 0.5 |  | 222100 |  |  |  | Analyze post-release quality for all products and the time of release | [21 empty] | 0
Open | 0.6 | 0 |  | 0.6 |  | 222200 |  |  |  | Review total number of defects found after 12 months during that year among software team | [21 empty] | 0
[6 empty] | 230000 |  | Submit A2 Deliverables
[6 empty] | 231000 |  |  | Create a DRAT workbook
Open | 0.2 | 0 |  | 0.2 |  | 231100 |  |  |  | Record the defect data | [21 empty] | 0
Open | 0.3 | 0 |  | 0.3 |  | 231200 |  |  |  | Conduct and record-refinement and analysis of the data. | [21 empty] | 0
Open | 0.1 | 0 |  | 0.1 |  | 232000 |  |  | Review DRT doc after update by teammate | [22 empty] | 0
Open | 0.5 | 0 |  | 0.5 |  | 233000 |  |  | Create Defect Analysis Report | [22 empty] | 0
Open | 0.2 | 0 |  | 0.2 |  | 234000 |  |  | Review the defect analysis report after updated by teammate | [22 empty] | 0
[6 empty] | 300000 | A3 - Cyclomatic Complexity and Flow Graph
[6 empty] | 310000 |  | Phase1
[6 empty] | 311000 |  |  | Main program analysis
Open | 0.5 | 0 |  | 0.5 |  | 311100 |  |  |  | Go thorough main program | [21 empty] | 0
Open | 0.3 | 0 |  | 0.3 |  | 311200 |  |  |  | Analyze the available tools to draw flowgraph | [21 empty] | 0
Open | 0.4 | 0 |  | 0.4 |  | 311300 |  |  |  | Produce a flowgraph | [21 empty] | 0
Open | 0.5 | 0 |  | 0.5 |  | 311400 |  |  |  | Compute and show calculation of cyclomatic complexity | [21 empty] | 0
[6 empty] | 312000 |  |  | C Program
Open | 0.7 | 0 |  | 0.7 |  | 312100 |  |  |  | Study Requirements Specification | [21 empty] | 0
Open | 0.9 | 0 |  | 0.9 |  | 312200 |  |  |  | Write C program that satisfies the Requirements Specification | [21 empty] | 0
Open | 0.5 | 0 |  | 0.5 |  | 312300 |  |  |  | Based on input parameters calculate output parameters | [21 empty] | 0
Open | 0.4 | 0 |  | 0.4 |  | 312400 |  |  |  | Produce a flowgraph | [21 empty] | 0
Open | 0.5 | 0 |  | 0.5 |  | 312500 |  |  |  | Compute and show calculation of cyclomatic complexity | [21 empty] | 0
[6 empty] | 313000 |  |  | Deliverables
Open | 0.1 | 0 |  | 0.1 |  | 313100 |  |  |  | A text file containing your C function | [21 empty] | 0
Open | 0.1 | 0 |  | 0.1 |  | 313200 |  |  |  | A Word file containing the phase 1 cover sheet | [21 empty] | 0
[6 empty] | 320000 |  | Phase2
[6 empty] | 321000 |  |  | Program 1
Open | 0.3 | 0 |  | 0.3 |  | 321100 |  |  |  | Review and note any errors | [21 empty] | 0
Open | 0.4 | 0 |  | 0.4 |  | 321200 |  |  |  | Produce a flowgraph | [21 empty] | 0
Open | 0.5 | 0 |  | 0.5 |  | 321300 |  |  |  | Compute and show calculation of cyclomatic complexity | [21 empty] | 0
Open | 0.4 | 0 |  | 0.4 |  | 321400 |  |  |  | Analyze and show how to correct errors | [21 empty] | 0
[6 empty] | 322000 |  |  | Program 2
Open | 0.3 | 0 |  | 0.3 |  | 322100 |  |  |  | Review and note any errors | [21 empty] | 0
Open | 0.4 | 0 |  | 0.4 |  | 322200 |  |  |  | Produce a flowgraph | [21 empty] | 0
Open | 0.5 | 0 |  | 0.5 |  | 322300 |  |  |  | Compute and show calculation of cyclomatic complexity | [21 empty] | 0
Open | 0.4 | 0 |  | 0.4 |  | 322400 |  |  |  | Analyze and show how to correct errors | [21 empty] | 0
[6 empty] | 323000 |  |  | Program 3
Open | 0.3 | 0 |  | 0.3 |  | 323100 |  |  |  | Review and note any errors | [21 empty] | 0
Open | 0.4 | 0 |  | 0.4 |  | 323200 |  |  |  | Produce a flowgraph | [21 empty] | 0
Open | 0.5 | 0 |  | 0.5 |  | 323300 |  |  |  | Compute and show calculation of cyclomatic complexity | [21 empty] | 0
Open | 0.4 | 0 |  | 0.4 |  | 323400 |  |  |  | Analyze and show how to correct errors | [21 empty] | 0
[6 empty] | 324000 |  |  | Deliverables for each program
Open | 0.2 | 0 |  | 0.2 |  | 324100 |  |  |  | Word file containing the phase 2 coversheet | [21 empty] | 0
Open | 0.1 | 0 |  | 0.1 |  | 324200 |  |  |  | Flowgraph | [21 empty] | 0
[6 empty] | 400000 | A4 - DMAIC and Root Cause Analysis
[6 empty] | 410000 |  | Define
Open | 0.6 | 0 |  | 0.6 |  | 411000 |  |  | Identify two CTQs (critical to quality measures) | [22 empty] | 0
[6 empty] | 420000 |  | Measure
[6 empty] | 421000 |  |  | Produce a swim lane diagram
Open | 0.5 | 0 |  | 0.5 |  | 421100 |  |  |  | Identify all organizations | [21 empty] | 0
Open | 0.4 | 0 |  | 0.4 |  | 421200 |  |  |  | Identify roles played by organisations | [21 empty] | 0
[6 empty] | 421300 |  |  |  | Determine order of things happened and dependencies
Open | 0.5 | 0 |  | 0.5 |  | 421310 |  |  |  |  | Create control flow diagram or flow chart. | [20 empty] | 0
[6 empty] | 421400 |  |  |  | Analyze the diagram to determine places in the process
Open | 0.4 | 0 |  | 0.4 |  | 421410 |  |  |  |  | Delays and work tasks which dont add any value | [20 empty] | 0
Open | 0.4 | 0 |  | 0.4 |  | 421420 |  |  |  |  | Unnecessary rework, complex processes, and other factors | [20 empty] | 0
[6 empty] | 430000 |  | Analyze
[6 empty] | 431000 |  |  | Come up with at least three root causes
Open | 0.4 | 0 |  | 0.4 |  | 431100 |  |  |  | Discuss the order in which these things should be addressed | [21 empty] | 0
Open | 0.5 | 0 |  | 0.5 |  | 431200 |  |  |  | Order these root causes based on impact | [21 empty] | 0
Open | 0.6 | 0 |  | 0.6 |  | 431300 |  |  |  | Produce a cause map (causal model) | [21 empty] | 0
[6 empty] | 432000 |  |  | Identify the three most important root causes
Open | 0.9 | 0 |  | 0.9 |  | 432100 |  |  |  | Produce a flow diagram of the sub-process that must be improved | [21 empty] | 0
Open | 0.5 | 0 |  | 0.5 |  | 433000 |  |  | Explain your recommendations | [22 empty] | 0
[6 empty] | 434000 |  |  | Deliverables
Open | 0.2 | 0 |  | 0.2 |  | 434100 |  |  |  | Single Word file containing DMAIC plan/status report | [21 empty] | 0
[6 empty] | 500000 | E1 - Study for Midterm Exam
[6 empty] | 510000 |  | Refer lecture videos, course materials on Blackboard, text book for modules 1 - 20
In Progress | 1.3 | 0.2 |  | 1.5 |  | 511000 |  |  | Modules 00-05 | [5 empty] | 2017-01-27: 0.2 |  | 0.2
Open | 1.4 | 0 |  | 1.4 |  | 512000 |  |  | Modules 06-10 | [22 empty] | 0
Open | 1.6 | 0 |  | 1.6 |  | 513000 |  |  | Modules 11-15 | [22 empty] | 0
Open | 1.5 | 0 |  | 1.5 |  | 514000 |  |  | Modules 16-20 | [22 empty] | 0
Open | 1.5 | 0 |  | 1.5 |  | 520000 |  | Prepare notes for modules 00 - 20 and study | [23 empty] | 0
Open | 2 | 0 |  | 2 |  | 530000 |  | Contact Prof, TA, Team mate for queries & doubts | [23 empty] | 0
[6 empty] | 600000 | E2 - Study for Final Exam
[6 empty] | 610000 |  | Refer lecture videos, course materials on Blackboard, text book for modules 21-40
Open | 1.5 | 0 |  | 1.5 |  | 611000 |  |  | Modules 21-25 | [22 empty] | 0
Open | 1.8 | 0 |  | 1.8 |  | 612000 |  |  | Modules 26-30 | [22 empty] | 0
Open | 1.5 | 0 |  | 1.5 |  | 613000 |  |  | Modules 21-35 | [22 empty] | 0
Open | 1.6 | 0 |  | 1.6 |  | 614000 |  |  | Modules 36-38 | [22 empty] | 0
Open | 1.6 | 0 |  | 1.6 |  | 620000 |  | Prepare notes for modules 21 - 38 and study | [23 empty] | 0
Open | 2 | 0 |  | 2 |  | 630000 |  | Contact Prof, TA, Team mate for queries & doubts | [23 empty] | 0
Spare Task Rows - For use in Inserting New Tasks and Sub-Tasks
[6 empty] | 90000 | Spare Parent Task - Top Level
[6 empty] | 99000 |  | Spare Parent Task - Second Level
[6 empty] | 99900 |  |  | Spare Parent Task - Third Level
Open |  | 0 |  |  |  | 91000 |  | Spare Sub-Task - Second Level | [23 empty] | 0
Open |  | 0 |  |  |  | 99100 |  |  | Spare Sub-Task - Third Level | [22 empty] | 0
Open |  | 0 |  |  |  | 99910 |  |  |  | Spare Sub-Task - Fourth Level | [21 empty] | 0
Totals >> | 55.8 | 6.6 |  | 63.2 |  | Total Actual Hours Worked >> | [8 empty] | 6.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| ^ | ^ | ^ | ^ | ^ | Cumulative Actual Hours (AC) >> | [8 empty] | 6.6 | 6.6 | 6.6 | 6.6 | 6.6 | 6.6 | 6.6 | 6.6 | 6.6 | 6.6 | 6.6 | 6.6 | 6.6 | 6.6 | 6.6 | 6.6 |  | 6.6
| Total Estimated Hours Remaining | Actual Hours So Far | Actual Completion Week | Total Hours Originally Estimated | Planned Completion Week | Estimated Hours Remaining (copy each week from total in column E) >> | [7 empty] | 63.2 | 2017-01-27: 55.8
| (copy to the right at the end of each week) | Should match Cumulative Actual Hours | (fill in when the task is complete) | Should match Cumulative Plan (PV) | [8 empty] | Week Number >> |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16
[6 empty] | Hours Earned This Week (enter each week) >> | [8 empty] | 55.8 1: 7.2
[6 empty] | Cumulative Hours Earned (EV) >> | [8 empty] | 7.2 | 7.2 | 7.2 | 7.2 | 7.2 | 7.2 | 7.2 | 7.2 | 7.2 | 7.2 | 7.2 | 7.2 | 7.2 | 7.2 | 7.2 | 7.2
[13 empty] | CPI |  | 1.0909 | 1.0909 | 1.0909 | 1.0909 | 1.0909 | 1.0909 | 1.0909 | 1.0909 | 1.0909 | 1.0909 | 1.0909 | 1.0909 | 1.0909 | 1.0909 | 1.0909 | 1.0909
[13 empty] | SPI |  | 1.8228 | 0.91139 | 0.60759 | 0.4557 | 0.36456 | 0.3038 | 0.2604 | 0.22785 | 0.20253 | 0.18228 | 0.16571 | 0.1519 | 0.14021 | 0.1302 | 0.12152 | 0.11392
[15 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2017 Spring