## Cover Sheet
ASSIGNMENT 1
DO INITIAL VERSION OF PERSONAL WBS
CSE 6329
Software Metrics and Quality Engineering
Spring, 2017
Name | <your name goes here>
ID | <indicate your student ID number here>
Points
(/10) Correct Format, including name on top, totals, etc.
(/50) Reasonable list of tasks for each assignment
(/40) Reasonable estimates, actual and earned hours.
(100) Total Assignment Grade
Comments from Grader
1

## Instructions
Instructions for Weekly WBS Entries
General Rules:
1: Cells with a white background are cells in which you may put a number or a task name at the appropriate time.
Some of these cells will change color when you put something there.
2: Cells with a colored background usually contain formulas that you should not change unless you are extending
the length of the course (which you may only do with the instructor's permission).
3: You may insert rows as needed to accommodate all of the tasks that you plan to do for the course.
(Use the spare tasks near the bottom to preserve the correct format and formulas.)
4: You should study every formula and every graph and understand what it is and why. This may be on an exam.
Step 1 - Enter hours worked each week
At the end of each week, fill in hours worked on each task, as follows:
(hours may be entered in whole hours, such as 2, or in tenths of an hour, such as 1.3)
For each task:
If you did no work on that task, do nothing.
If you worked on that task during the past week:
Enter total hours worked on the task in the column corresponding to the current week (column U through AJ).
Cell should change color when you enter a non-zero value.
Enter total hours of work remaining on the task in column E:
If the task is complete, enter 0 hours remaining.
The total hours remaining is your best current estimate, which may differ from what was originally estimated.
Step 2: Check for errors
Review all totals and numbers and make sure everything seems correct.
Make corrections as necessary
If the graphs (charts) look strange, something is wrong. Figure out what's wrong and fix it.
Step 3: Record Estimated Hours Remaining at end of current week
Copy the "total estimated hours remaining" (bottom of column E) to estimated hours remaining cell for current week
Cell will change color
This will update the burndown and burnup charts
Step 4: Update Earned Value
The hours earned this week row for the current week (near the bottom) should start off with blank or 0.
For each task that has completed during the current week:
Find the originally estimated hours for that task and add it to the hours earned this week for the current week
When done, this total will be the earned value for the week and will update the earned value chart accordingly.

## WBS
|  | PWBS | [8 empty] | Planned Effort |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
Open | 2017 sp | CSE 6329-002 | Schedule | [7 empty] | Cumulative Plan (PV) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
In Progress | <Name of Student> | [9 empty] | Estimated Effort Remaining | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Complete | Actual Results |  |  | Estimates |  | WBS | [6 empty] | Actual Hours Worked and Earned
Status | Estimated Hours Remaining | Actual Hours So Far | Actual Completion Week | Estimated Hours of Effort | Planned Completion Week | Task # |  |  |  |  | Task Description Week Ending >> |  | 2017-01-27 | 2017-02-03 | 2017-02-10 | 2017-02-17 | 2017-02-24 | 2017-03-03 | 2017-03-10 | 2017-03-17 | 2017-03-24 | 2017-03-31 | 2017-04-07 | 2017-04-14 | 2017-04-21 | 2017-04-28 | 2017-05-05 | 2017-05-12 | insert new column here | Total Hours Worked
[6 empty] | 10000 | A1 - Develop PWBS
[6 empty] | 11000 |  | Read and Analyze A1 SOW for PWBS
Open |  | 0 |  |  |  | 11100 |  |  | List tasks to be performed | [20 empty] | 0
Open |  | 0 |  |  |  | 11200 |  |  | Estimate hours required for each task | [20 empty] | 0
Open |  | 0 |  |  |  | 11300 |  |  | Break into smaller sub-tasks as required | [20 empty] | 0
Open |  | 0 |  |  |  | 11400 |  |  | Modify template to add tasks and correct formulas/coloring | [20 empty] | 0
Open |  | 0 |  |  |  | 11500 |  |  | Record estimated hours in Estimated Hours of Effort column | [20 empty] | 0
[6 empty] | 12000 |  | Read and Analyze A2 SOW
Open |  | 0 |  |  |  | 12100 |  |  | List tasks to be performed | [20 empty] | 0
Open |  | 0 |  |  |  | 12200 |  |  | Estimate hours required for each task | [20 empty] | 0
Open |  | 0 |  |  |  | 12300 |  |  | Break into smaller sub-tasks as required | [20 empty] | 0
Open |  | 0 |  |  |  | 12400 |  |  | Modify template to add tasks and correct formulas/coloring | [20 empty] | 0
Open |  | 0 |  |  |  | 12500 |  |  | Record estimated hours in Estimated Hours of Effort column | [20 empty] | 0
[6 empty] | 13000 |  | Read and Analyze A3 SOW
Open |  | 0 |  |  |  | 13100 |  |  | List tasks to be performed | [20 empty] | 0
Open |  | 0 |  |  |  | 13200 |  |  | Estimate hours required for each task | [20 empty] | 0
Open |  | 0 |  |  |  | 13300 |  |  | Break into smaller sub-tasks as required | [20 empty] | 0
Open |  | 0 |  |  |  | 13400 |  |  | Modify template to add tasks and correct formulas/coloring | [20 empty] | 0
Open |  | 0 |  |  |  | 13500 |  |  | Record estimated hours in Estimated Hours of Effort column | [20 empty] | 0
[6 empty] | 14000 |  | Read and Analyze A4 SOW
Open |  | 0 |  |  |  | 14100 |  |  | List tasks to be performed | [20 empty] | 0
Open |  | 0 |  |  |  | 14200 |  |  | Estimate hours required for each task | [20 empty] | 0
Open |  | 0 |  |  |  | 14300 |  |  | Break into smaller sub-tasks as required | [20 empty] | 0
Open |  | 0 |  |  |  | 14400 |  |  | Modify template to add tasks and correct formulas/coloring | [20 empty] | 0
Open |  | 0 |  |  |  | 14500 |  |  | Record estimated hours in Estimated Hours of Effort column | [20 empty] | 0
Open |  | 0 |  |  |  | 15000 |  | Enter Actual and Earned Hours for week ending 1/27 | [21 empty] | 0
Open |  | 0 |  |  |  | 15100 |  | Submit A1 (Draft) | [21 empty] | 0
Open |  | 0 |  |  |  | 16000 |  | Review comments from TA/Instructor and Correct Mistakes | [21 empty] | 0
[6 empty] | 17000 |  | Make Weekly Updates to Actual and Earned Hours in PWBS
Open |  | 0 |  |  |  | 17100 |  |  | Updates for 2/3 | [20 empty] | 0
Open |  | 0 |  |  |  | 17200 |  |  | Updates for 2/10 | [20 empty] | 0
Open |  | 0 |  |  |  | 17300 |  |  | Updates for 2/17 | [20 empty] | 0
Open |  | 0 |  |  |  | 17400 |  |  | Updates for2/24 | [20 empty] | 0
Open |  | 0 |  |  |  | 17500 |  |  | Updates for 3/3 | [20 empty] | 0
Open |  | 0 |  |  |  | 17600 |  |  | Updates for 3/10 | [20 empty] | 0
Open |  | 0 |  |  |  | 17700 |  |  | Updates for 3/17 | [20 empty] | 0
Open |  | 0 |  |  |  | 17800 |  |  | Updates for 3/24 | [20 empty] | 0
Open |  | 0 |  |  |  | 17900 |  |  | Updates for 3/31 | [20 empty] | 0
Open |  | 0 |  |  |  | 17910 |  |  | Updates for 4/7 | [20 empty] | 0
Open |  | 0 |  |  |  | 17920 |  |  | Updates for 4/14 | [20 empty] | 0
Open |  | 0 |  |  |  | 17930 |  |  | Updates for 4/21 | [20 empty] | 0
Open |  | 0 |  |  |  | 17940 |  |  | Updates for 4/28 | [20 empty] | 0
Open |  | 0 |  |  |  | 18000 |  | Submit Final PWBS | [21 empty] | 0
[6 empty] | 20000 | A2
[6 empty] | 21000 |  | First Task for A2
Open |  | 0 |  |  |  | 21100 |  |  | First subtask | [20 empty] | 0
Open |  | 0 |  |  |  | 21200 |  |  | Secondsubtask | [20 empty] | 0
[6 empty] | 22000 |  | Second Task for A2
Open |  | 0 |  |  |  | 22100 |  |  | Fill in new rows as needed for other tasks and subtasks | [20 empty] | 0
Open |  | 0 | [5 empty] | Fill in new rows as required | [21 empty] | 0
[6 empty] | 30000 | A3
[6 empty] | 40000 | A4
Open |  | 0 |  |  |  | 50000 | E1 - Study for Midterm Exam | [22 empty] | 0
Open |  | 0 |  |  |  | 60000 | E2 - Study for Final Exam | [22 empty] | 0
Spare Task Rows - For use in Inserting New Tasks and Sub-Tasks
[6 empty] | 90000 | Spare Parent Task - Top Level
[6 empty] | 99000 |  | Spare Parent Task - Second Level
[6 empty] | 99900 |  |  | Spare Parent Task - Third Level
Open |  | 0 |  |  |  | 91000 |  | Spare Sub-Task - Second Level | [21 empty] | 0
Open |  | 0 |  |  |  | 99100 |  |  | Spare Sub-Task - Third Level | [20 empty] | 0
Open |  | 0 |  |  |  | 99910 |  |  |  | Spare Sub-Task - Fourth Level | [19 empty] | 0
Totals >> | 0 | 0 |  | 0 |  | Total Actual Hours Worked >> | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| ^ | ^ | ^ | ^ | ^ | Cumulative Actual Hours (AC) >> | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
| Total Estimated Hours Remaining | Actual Hours So Far | Actual Completion Week | Total Hours Originally Estimated | Planned Completion Week | Estimated Hours Remaining (copy each week from total in column E) >> | [5 empty] | 0
| (copy to the right at the end of each week) | Should match Cumulative Actual Hours | (fill in when the task is complete) | Should match Cumulative Plan (PV) | [6 empty] | Week Number >> |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16
Hours Earned This Week (enter each week) >>
[6 empty] | Cumulative Hours Earned (EV) >> | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[11 empty] | CPI |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
[11 empty] | SPI |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
[13 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2017 Spring